## Dashboard
NGFW Maturity Engagement – Dashboard
Project Start
Project End
Total Working Days
Working Days Elapsed
Schedule Elapsed %
Overall % Complete
Tasks Late / Late Start
Open High Risks
Phase Summary
Phase | Start | Finish | Work Days | % Complete | Status
Methodology: Weeks 1–4 Discovery → Gaps → Future State → Roadmap & Readout ¦ Weeks 5–16 Remediation → Validation & Closeout

## Project Plan
NGFW Maturity Engagement – Project Plan
Week of (Mon)
WBS | Phase / Task | Owner | Start | Finish | Work Days | % Complete | Status | Predecessor | Deliverable / Output | Notes | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
0 | Project Mobilization & Governance
0.1 | Contract / SOW confirmation & resourcing | Consultant | 2026-09-14 | 2026-09-15 |  | 100% |  |  | SOW baseline
0.2 | Kickoff meeting & stakeholder alignment | Joint | 2026-09-16 | 2026-09-16 |  | 100% |  | 0.1 | Kickoff deck, stakeholder map
0.3 | Data request & access provisioning (configs, diagrams, tooling) | Client | 2026-09-16 | 2026-09-18 |  | 100% |  | 0.2 | Data request tracker
0.4 | Weekly status reporting & steering committee (recurring) | Consultant | 2026-09-21 | 2026-12-31 |  | 15% |  | 0.2 | Weekly status reports
1 | Phase 1 – Discovery (Current State)
1.1 | Stakeholder interviews (NetSec, NetEng, SecOps, GRC, App owners) | Consultant | 2026-09-16 | 2026-09-22 |  | 100% |  | 0.2 | Interview notes
1.2 | Firewall inventory: platforms, versions, HA, licensing, EoL/EoS | Joint | 2026-09-16 | 2026-09-22 |  | 100% |  | 0.3 | Asset inventory
1.3 | Configuration & rulebase collection / export | Client | 2026-09-16 | 2026-09-21 |  | 100% |  | 0.3 | Config exports
1.4 | Topology & segmentation mapping (DC, campus, cloud, remote/SASE) | Consultant | 2026-09-21 | 2026-09-24 |  | 100% |  | 1.2 | Draft topology
1.5 | Operational process & tooling review (change mgmt, SIEM, NAC, IdP) | Consultant | 2026-09-22 | 2026-09-25 |  | 100% |  | 1.1
1.6 | DELIVERABLE: Firewall Estate Architecture (current state) | Consultant | 2026-09-24 | 2026-09-29 |  | 70% |  | 1.4 | D1 – Firewall Estate Architecture
2 | Phase 2 – Identify Pain Points, Issues & Gaps
2.1 | Rulebase hygiene analysis (shadowed, unused, any/any, overly permissive) | Consultant | 2026-09-23 | 2026-09-29 |  | 50% |  | 1.3
2.2 | NGFW feature utilization review (App-ID, User-ID, TLS decryption, IPS, URL, sandboxing) | Consultant | 2026-09-23 | 2026-09-29 |  | 50% |  | 1.3
2.3 | Maturity scoring (NIST CSF / CIS / vendor best practice) & lifecycle risk review | Consultant | 2026-09-28 | 2026-10-01 |  | 10% |  | 1.6 | Maturity scorecard
2.4 | Gap & pain-point validation workshop | Joint | 2026-10-01 | 2026-10-01 |  | 0% |  | 2.3 | Workshop output
2.5 | DELIVERABLE: Problem Areas & Gaps Assessment document | Consultant | 2026-09-30 | 2026-10-02 |  | 0% |  | 2.4 | D2 – Gaps Assessment
3 | Phase 3 – Define Future State Vision
3.1 | Requirements, guiding principles & target architecture options | Consultant | 2026-09-30 | 2026-10-02 |  | 0% |  | 2.4 | Options analysis
3.2 | Future-state vision workshop & option selection | Joint | 2026-10-05 | 2026-10-05 |  | 0% |  | 3.1 | Decision log
3.3 | Future-state architecture, target operating model & maturity targets | Consultant | 2026-10-05 | 2026-10-06 |  | 0% |  | 3.2 | Future-state architecture
4 | Phase 4 – Remediation Plan & Modernization Roadmap
4.1 | Gap-to-initiative mapping, prioritization & sequencing | Joint | 2026-10-05 | 2026-10-07 |  | 0% |  | 3.2 | Prioritization matrix
4.2 | DELIVERABLE: Modernization Roadmap (incl. remediation plan) | Consultant | 2026-10-07 | 2026-10-08 |  | 0% |  | 4.1 | D3 – Modernization Roadmap
4.3 | Milestone: Executive readout – D1, D2, D3 presented & accepted | Joint | 2026-10-09 | 2026-10-09 |  | 0% |  | 4.2 | Executive readout deck
5 | Phase 5 – Remediation Mobilization
5.1 | Detailed remediation work plan, change windows & CAB scheduling | Joint | 2026-10-13 | 2026-10-15 |  | 0% |  | 4.3 | D4 – Remediation Execution Plan
5.2 | Config backups, rollback procedures & test / validation plans | Consultant | 2026-10-13 | 2026-10-16 |  | 0% |  | 4.3 | Rollback & test plans
5.3 | Milestone: Remediation go / no-go | Joint | 2026-10-16 | 2026-10-16 |  | 0% |  | 5.1
6 | Phase 6 – Remediation Execution
6.1 | Quick wins: rulebase cleanup (unused, shadowed, any/any, redundant objects) | Joint | 2026-10-19 | 2026-11-06 |  | 0% |  | 5.3 | Cleanup change records
6.2 | Software / firmware upgrades & EoL/EoS hardware remediation | Joint | 2026-10-26 | 2026-11-20 |  | 0% |  | 5.3 | Upgrade change records
6.3 | Logging, SIEM integration & monitoring / alerting tuning | Consultant | 2026-10-26 | 2026-11-13 |  | 0% |  | 5.3
6.4 | Enable NGFW security profiles (App-ID migration, User-ID, IPS, URL, sandboxing) | Joint | 2026-11-02 | 2026-12-04 |  | 0% |  | 6.1
6.5 | Segmentation & zone redesign (zero trust alignment) | Joint | 2026-11-09 | 2026-12-11 |  | 0% |  | 6.1
6.6 | Phased TLS/SSL decryption rollout | Joint | 2026-11-16 | 2026-12-11 |  | 0% |  | 6.4
6.7 | Policy lifecycle, change process & automation (policy-as-code, reviews) | Consultant | 2026-11-02 | 2026-12-04 |  | 0% |  | 5.3 | Updated process docs
6.8 | Milestone: Horizon 1 remediation complete | Joint | 2026-12-18 | 2026-12-18 |  | 0% |  | 6.6
7 | Phase 7 – Validation & Closeout
7.1 | Post-remediation validation, testing & maturity re-score | Consultant | 2026-12-14 | 2026-12-18 |  | 0% |  | 6.5 | Validation results
7.2 | DELIVERABLE: Post-Remediation Report & as-built architecture | Consultant | 2026-12-16 | 2026-12-22 |  | 0% |  | 7.1 | D5 – Post-Remediation Report
7.3 | Knowledge transfer, runbooks & handover | Consultant | 2026-12-21 | 2026-12-23 |  | 0% |  | 7.2 | Handover package
7.4 | Final status report & closeout | Consultant | 2026-12-28 | 2026-12-30 |  | 0% |  | 7.3 | Closeout report
7.5 | Milestone: Project close | Joint | 2026-12-31 | 2026-12-31 |  | 0% |  | 7.4
OVERALL ENGAGEMENT
Gantt legend:
Phase
Task
Deliverable
Milestone
Current week (header)
% Complete values reflect status as of Sep 28, 2026 (week 3) – update weekly.

## Deliverables
Engagement Deliverables
ID | Deliverable | Description / Key Contents | Format | Plan WBS | Draft Due | Final Due | Client Approver | Status
D1 | Firewall Estate Architecture | Current-state inventory (platforms, versions, HA, licensing, EoL); logical & physical topology; zones/segmentation; traffic flows; management plane & integrations (SIEM, IdP, NAC, orchestration). | Visio/PDF + Excel inventory | 1.6 |  |  | Network Security Lead
D2 | Problem Areas & Gaps Assessment | Pain points from interviews; rulebase hygiene findings; NGFW feature-utilization gaps; lifecycle/capacity risks; process & tooling gaps; maturity scorecard (current vs. target) with risk ratings. | Word/PDF report | 2.5 |  |  | CISO
D3 | Modernization Roadmap | Future-state vision & target architecture; remediation initiatives mapped to gaps; prioritization; phased sequencing (0–3 / 3–12 / 12–24 mo); budget ranges, resourcing, KPIs. | PowerPoint + Excel roadmap | 4.2 |  |  | CISO
S1 | Executive Readout | Presentation of D1, D2 and D3 to steering committee; approval to proceed with remediation. | PowerPoint | 4.3 |  |  | Executive Sponsor
D4 | Remediation Execution Plan | Detailed work packages, change windows, CAB schedule, rollback and test plans for in-engagement remediation. | Excel + Word | 5.1 |  |  | Network Security Lead
D5 | Post-Remediation Report | Validation results, maturity re-score vs. baseline, as-built architecture, remaining roadmap items. | Word/PDF + Visio | 7.2 |  |  | CISO
Draft Due = 1 working day before final (assumption: client review window). Green = linked to Project Plan.

## Milestones
Key Milestones
WBS | Milestone | Date | Days from Today | Status
0.2
1.6
2.5
4.2
4.3
5.3
6.8
7.2
7.5

## RACI
RACI Matrix
Activity | Engagement Lead | NGFW Architect | Security Analyst | Client Sponsor / CISO | Client NetSec Team | Client SecOps / GRC
Mobilization & governance | A | C | I | R | C | I
Discovery & data collection | A | R | R | I | C | C
D1 Firewall Estate Architecture | A | R | C | I | C | I
D2 Problem Areas & Gaps Assessment | A | R | R | C | C | C
Future-state vision | R | R | C | A | C | C
D3 Modernization Roadmap | A | R | C | C | C | I
Executive readout (D1–D3) | R | C | I | A | I | I
D4 Remediation Execution Plan | A | R | C | C | R | C
Remediation execution & change implementation | A | R | R | I | R | C
Validation & D5 Post-Remediation Report | A | R | R | C | C | C
R = Responsible · A = Accountable · C = Consulted · I = Informed

## Risks & Issues
RAID – Risks & Issues Log
ID | Type | Description | Impact (1-5) | Likelihood (1-5) | Score | Rating | Mitigation | Owner | Status
R1 | Risk | Delayed access to firewall configs / management consoles | 4 | 3 |  |  | Escalate via sponsor at kickoff; track in data request log | Client | Open
R2 | Risk | Stakeholder availability for interviews/workshops | 3 | 3 |  |  | Schedule all sessions in first 2 weeks; offer async questionnaires | Engagement Lead | Open
R3 | Risk | Compressed 4-week assessment limits review time for D1–D3 | 4 | 3 |  |  | Daily working sessions; pre-schedule readout for Oct 9; drafts shared incrementally | Engagement Lead | Open
R4 | Risk | Remediation changes cause outages or business disruption | 5 | 2 |  |  | CAB approval, maintenance windows, tested rollback, staged rollout | NGFW Architect | Open
R6 | Risk | Limited change windows / holiday change freeze (late Nov, Dec) | 4 | 4 |  |  | Front-load high-impact changes Oct–mid Nov; confirm freeze dates | Client | Open
R5 | Risk | Incomplete CMDB / undocumented firewalls (shadow estate) | 3 | 3 |  |  | Validate inventory against network scans & routing tables | NGFW Architect | Open
I1 | Issue | Config export for cloud firewalls pending security approval | 3 | 5 |  |  | Sponsor escalation requested | Client | Open

## Inputs
NGFW Maturity Engagement – Project Inputs
Client | Customer
Engagement | Next-Generation Firewall (NGFW) Maturity Assessment
Project Start | 2026-09-14
Project End | 2026-12-31
Status Date (As-Of)
Engagement Lead | Engagement Lead
Client Sponsor | CISO
Legend
Yellow fill / blue text | Editable input (dates, owners, % complete, status notes)
Black text | Formula – do not overwrite
Holidays (excluded from working days)
2026-10-12 | Columbus / Indigenous Peoples' Day
2026-11-11 | Veterans Day
2026-11-26 | Thanksgiving
2026-11-27 | Day after Thanksgiving
2026-12-24 | Christmas Eve
2026-12-25 | Christmas Day
Assumption: US holiday calendar; adjust to client calendar as needed.